## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 2024-04-29 13:30
Group Number |  | 4
Participant 1 |  | Akinrinlola Akintayo
Participant 2 |  | Anthony Kodzo Kevin
Participant 3 |  | Nasr Mohamed
Participant 4 |  | Najfar Raphael
Participant 5 |  | Asaad Abanob
Mentor |  | Rohatsch Lukas
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Index.html (basic layout) | 2 | 1 | -1 | 1
2 | Github Repository for the project | 3 | 1 | -2 | 1
3 | Footer (without styling) | 1 | 0.5 | -0.5 | 1
4 | Impressum (without styling) | 2 | 2 | 0 | 1
5 | Help page (without styling) | 2 | 1 | -1 |  | 1 | is not finished yet
6 | Navbar (without styling) | 1 | 1 | 0 | 1
|  | 11 | 6.5 | -4.5 | 5 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol